## Slide 1: PREPARED Workbook
Kathy Castagna, EPA Region 1
Mark Lewis, CT DEEP
John Podgurski, EPA Region 1
March 25, 2015

## Slide 2: Purpose and Overview

## Slide 3: PREPARED
A risk management tool to help cities and towns decide the best approach to brownfield redevelopment
Provides worksheets to guide the process
Use is optional

## Slide 4: Why USE It?
Provides a structure for thinking about potential municipal involvement in a reuse project
Improves communication within & outside team (i.e., increases efficiency and effectiveness), including:
  Environmental consultants
  Legal counsel
  Municipal departments
  General public
  Developers/financial institutions
Documents key considerations and decisions
  Promotes clarity and transparency
  Builds support for decisions
  Brings new- and non-team members up to speed

## Slide 5: Risk Management Framework
Risk-Based Decisions
  identify each risk
  evaluate its likelihood and consequences
  select an appropriate action to control risks
  implement the action to achieve the desired outcome
  Typically an iterative process involving the gathering and evaluating of information!!
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action
PREPARED mirrors this decision process

## Slide 6: Worksheets
Helps guide and document the process
You don’t have to fill out every one
You don’t have to fill them in completely
Worksheets
1a Stakeholder Information
1 Establish Project Goals
2 Evaluate Potential Property Reuse Options
3 Identify Property Recovery Actions
4 Summarize Due Diligence
5 Identify Obstacles and Risks
6a Financial Analysis, Sources and Uses
6 Options to Manage Risks
7 Project Status
8 Project Summary

## Slide 7: Establish Project Goals
Goals drive the process
Gain early consensus
Key considerations
  what is the desired outcome?
  how important is reuse?
  how time critical is reuse?
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action
“If you don’t know where you’re going any road will get you there”…Lewis Carroll from Alice in Wonderland

## Slide 8: Preliminary Reuse Assessment
Obtain information to understand
  Status of property
  Physical and social opportunities and constraints
  Community needs and potential impacts
  Market and extent of demand
  Potential alternatives for reuse
  General cost constraints
  Potential for success and level of risk
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 9: Identify Property Recovery Actions
Actions that involve a municipality in the cleanup and reuse of a contaminated property
Each action carries its own set of issues that impact the strategy for managing project risks
More Control
Less Liability
Acquisition and long term ownership
Acquisition and interim ownership
Leasing by municipality
Acquisition and “simultaneous” transfer to a third party
Collaboration with the property owner
Transfer tax liens
Incentives to promote reuse
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 10: Conduct Due Diligence
Essential step in identifying and evaluating project risks
  Understand potential impediments to reuse
    presence of hazardous substances on the property
    reuse obstacles and potential sources of project risk
  May protect against potential environmental liability
    all appropriate inquiry is required for some types of liability protection under CERCLA
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 11: Identify Property Reuse Obstacles
Anything that would affect the decision to redevelop a property
  economic limitations
  legal challenges
  regulatory hurdles
  community concerns
  development issues
  management considerations
Utilizes information obtained through the due diligence process
Process of identifying is iterative
Prioritize based on how it impacts the project goals
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 12: Assess Property Reuse Risks
Obstacles generally are associated with a risk
Risk refers to the probability that an adverse event will occur and the consequences of that adverse event
          legal
          financial
          community issues & acceptance
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 13: Identify Risk Management Options
Risk can’t always be eliminated — only managed
Reduce the probability and impact of a risk
Risk mgt. creates opportunities
            avoid
            reduce
            transfer
            share
            accept
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action
Consequence
Probability
Risk Management

## Slide 14: Resolving Data Gaps
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action
Resolve Data Gaps
Uncertainty drives risk
How much information is enough?

## Slide 15: Select a Property Recovery Action
Would you move forward with this site?
  have obstacles been (or can be) identified?
  have risks been (or can be) resolved?
  are the necessary resources available?
  is the project financially viable and realistic?
  is additional information needed?
What alternative (property recovery action) would you select?
Stakeholder Engagement
Establish Goals
Pre-Screen Property Recovery Actions
  Property Reuse Assessment
Conduct Due Diligence
Identify Property Reuse Obstacles
Assess Property Reuse Risks
Manage Property Reuse Risks
Select Property Recovery Action

## Slide 16: PREPARED: The Next Generation
The Connecticut DEEP PREPARED Municipal Website Interface

## Slide 17: CT DEEP Web-Enabled PREPARED Workbook
PREPARED Workbook
  Currently only available on EPA Region 1 webpage as a downloadable document
  Not state-specific
Connecticut is the first state to web-enable the PREPARED Workbook (Joint CT DEEP/ EPA Region 1 Project)
  Improves PREPARED access and usability
  Is state-specific- links to Connecticut information & programs
  Not a CT DEEP or EPA requirement
Planned launch in April
Check DEEP website- www.ct.gov/deep for rollout announcement
Hopefully a model for other states

## Slide 18: Questions/COMMENTS?
Mark Lewis
Brownfields Coordinator
CT Dept. of Energy and Environment (860) 424-3768
mark.lewis@ct.gov
Kathy Castagna
Brownfields Project Officer
U.S. EPA Region 1
(617) 918-1429
castagna.kathy@epa.gov
John Podgurski
Chief, Brownfields Section
U.S. EPA Region 1
(617) 918-1429
podgurski.john@epa.gov
Accessing PREPARED
EPA Region 1Webpage: www.epa.gov/region1/brownfields/prepared
CT DEEP Webpage: Launching soon on www.ct.gov/deep/remediation